## Sheet1
Milestone | Owner | Cost (days) | Progress | Remaining (days) | Area | Feature | Description
My Buffer (workdays)
0
0
[5 empty] | Deadline | Remaining (workdays) | Critical Path Buffer (workdays) | 0
M1 Total |  | 14 | 100% | 0 | 2022-10-07 | 0 | 0
M2 Total |  | 31 | 100% | 0 | 2022-11-28 | 0 | 0
M3 Total |  | 10 | 100% | 0 | 2022-12-16 | 0 | 0
| Total dev days: | 55 | 100% | 0