## Sheet1
Milestone | Owner | Cost (days) | Progress | Remaining (days) | Area | Feature | Description
M1 | Adi, Ryan, Arthur | 1 | 1 | 0 | Initial Meeting | Client Meeting | Meeting with the Client
M1 | Adi, Ryan, Arthur | 5 | 5 | 0 | Learning | HTML | Learning HTML and how to code for our website
M1 | Adi, Ryan, Arthur | 5 | 5 | 0 | Learning | JavaScript | Learning JavaScript and how to use it for our website
M1 | Adi, Ryan | 3 | 3 | 0 | Learning | Survey Form | Learning hwo to code a form that can recognize responses given to it by the user
M2 | Adi, Ryan | 7 | 7 | 0 | Learning | Database | Learn how to use Microsoft Azure and how to create a database
M2 | Arthur VDH | 5 | 5 | 0 | Frontend | Index Page | Create and code the index page for the website. Ie: Inputting the ram logo, the "in memorium" section, activities section, and even details
M2 | Arthur VDH | 5 | 5 | 0 | Backend | Database | Create a functioning Database using Google forms as an initial solution to a database that the client can use to see the responses and who is attending
M2 | Corliss Glover | 1 | 1 | 0 | Backend | Domain | Pay for a domain that allows us to publish the website on the internet, allowing anyone to access it
M3 | Adi, Ryan | 5 | 3 | 2 | Learning | Database | Learn how to connect out databasae to our website
M3 | Adi, Ryan | 5 | 0 | 5 | Learning | Database | Learn how to input user data from the website into the database
M3 | Adi, Ryan | 5 | 3 | 2 | Learning | Web API | Learn what a Web API is and how to apply it to our website and database
M1 Total | 14
M2 Total | 21
M3 Total | 15 |  |  |  | Deadline | Remaining (workdays) | Critical Path Buffer (workdays) | My Buffer (workdays)
[5 empty] | 2023-03-17 | 0 | 0 | 0
[5 empty] | 2023-04-15 | 0 | 0 | 0
| Total dev days: | 47 | 81% | 9 | 2023-05-26 | 9 | 0 | 0